## Lessons Learned Template
Lessons Learned Template
Today's Date: | 2023-04-27
Project Name: | AI in Agriculture
Project Manager: | Emmett Pierson
Notes: | This is all made up and its quite hard to think of things
WIN or ISSUE | Describe What Happened | What Was the Impact? | How Does This Change Future Projects? | Action Items
ISSUE | Project manager underestimated how much manpower it would take to install each system. | The budget had to be increased very early on in the project's lifecycle. | Project managers have to pull from more resources when estimating project costs, with knowledge from experienced peers being preferable. | Providing training on how to estimate in fields one may not be familiar with, and how to find people that are experienced.
WIN | Openness of communication ensured farmers were willing to embrace the changes. | The consultants and analysts had more freedom to experiement to try and improve various aspects of the system as new developments arose. | Increasing communications when doing study type projects may increase the participants willingness to make changes partway through. | Providing training on how to communicate in the way that your participants prefer.
ISSUE | The recruitment of farmers past the initial two was harder and took longer than anticipated. | Even though the installation process went smoothly on each farm, the weekly goal of a completed farm per week was not able to be kept up with. | Ensuring the proper sample size is available from the onset of the project to prevent delays. | Not approving study type projects that don't have proper participant numbers and/or an method to obtain those particpants until the requirement is met.
WIN | The analysts were able to finish the report before the offical end of the project due to having enough time during the project. | The project was completed months earlier than anticipated and the labor budget was lower than expected. | Allowing adequate time and manpower from the beginning of a project allows for people to plan ahead and complete tasks early, without having to work overtime. | Providing training on how to estimate in fields one may not be familiar with, and how to find people that are experienced. (same as on line 9)

## How to Use This Template
How to Use Our Lessons Learned Template
The lessons learned template is a tool to note what worked and what didn't in your project to repeat the positive and avoid the negative.
Today's Date: Enter today’s date
Project Name: Give your project a name, so it can be quickly identified
Project Manager: Enter the name of the person overseeing the project. This could be a proper project manager or any staff member who is the owner of the work.
Notes: This field is for you to add any relevant information you’d like. Ideas: client name, stakeholders, project summary, budget, etc.
WIN or ISSUE: Choose either WIN or ISSUE to classify the lesson. A win is something positive that happened, and an issue is something negative that happened
Describe What Happened: Use this field to give a detailed description of the lesson you learned
What Was the Impact?: Here, you’ll describe the positive or negative result, and the impact there may have been. For a win, write about the positive outcome that occurred. For an issue, write about the negative consequences you experienced due to the problem
How Does This Change Future Projects?: In this field, record your thoughts on how this lesson might impact future work. Think about how other people in your organization might benefit from learning this lesson
Action Items: Add the actionable steps that will be taken to address your win or issue. Every row should have an action item, even if it is as simple as “monitor to see if it happens again.” This is the most important part of the template, because you are outlining the steps you will take to improve